## Responsibilities
MEME DDI Responsibilities
Category | Responsibility | # | Description | Department | SI Vendor | Module Vendor
Project Management | Strategic Alignment | 1 | Confirm alignment between executive stakeholder vision/priorities and project scope/schedule | Primary | As Needed | As Needed
| Methodology Definition | 2 | Define tracking, execution, and reporting processes, procedures, standards - including SDLC | Primary | Secondary | As Needed
| Methodology Adherence | 3 | Ensure project staff adherence to project processes, procedures, standards | Primary | Secondary | As Needed
| Org Structure | 4 | Define the project org chart, manage changes to team structures as needed | Primary | Secondary | As Needed
| Risk/Issue/Decision Management | 5 | Escalate/mitigate risks and issues; facilitate/communicate decisions | Primary | Secondary | As Needed
| Plan Development | 6 | Deliver/maintain project management plan documentation (PM Plan, Test Plan, Communications Plan, Implementation Plan, Conversion Plan, Interface Plan, Code/configuration management plan, etc.) | Primary | Secondary | As Needed
| Plan Management | 7 | Manage teams and work efforts to deliver on the plan / critical path | Primary | Secondary | As Needed
| Progress Reporting | 8 | Report project status | Primary | Secondary | As Needed
| Financials Tracking | 9 | Manage budgets, forecasts, consumed, actuals, including match funding tracking | Primary | As Needed | As Needed
| Vendor management | 10 | Manage vendor procurements, contracts, and delivery performance | Primary | - | -
| Communications | 43 | Maintain appropriate communication with stakeholders and project teams | Primary | Secondary | As Needed
| Policies, Processes, and Standards | 11 | Define and enforce project policies, processes, and standards | Primary | Secondary | As Needed
Certification | CMS Requirements Adherence | 12 | Ensure project scope/activities adhere to CMS requirements | Primary | Secondary | As Needed
| CMS Funding | 13 | Submit funding match requests for CMS approval and annual updates | Primary | As Needed | As Needed
| MECL Milestones | 14 | Facilitate completion of MECL Milestones | Primary | As Needed | As Needed
| MECT Checklist Traceability | 15 | Define and maintain traceability between MECT checklists and project delivery artifacts | Primary | As Needed | As Needed
| MITA | 16 | Ensure compliance with MITA plan / conditions | Primary | Secondary | Secondary
Scope Management | Define Vision/Approach | 17 | Determine project phases and high-level scope of each phase | Primary | Secondary | As Needed
| Roadmap Planning | 18 | Identify the deliverables / activities and associated sequencing required to complete each phase and the associated DoD of each | Primary | Secondary | As Needed
| Scope Planning | 19 | Decompose deliverables into tangible milestones and the associated DoD of each | Primary | Secondary | As Needed
| Iteration Planning | 20 | Identify tasks achievable during the next iteration | Primary | Secondary | Secondary
Delivery | Enterprise Architecture | 21 | Design the business, technical, and information architecture for the future-state system by phase | Primary | As Needed | As Needed
| Application Architecture | 45 | Design components within the enterprise architecture | Secondary | Primary | As Needed
| Blocker Resolution | 22 | Manage the escalation and resolution of team-level blockers and impediments | Primary | Secondary | As Needed
| Requirements Elicitation | 23 | Capture specific policy, operational, and technical requirements from State SMEs | Primary | Secondary | Secondary
| Solution Design | 24 | Design the system specifications needed to meet the business requirements | Secondary | Primary | Secondary
| Product Configuration | 44 | Update product configurations to meet the business requirements | Primary | As Needed | Secondary
| Code Development | 26 | Develop interfaces and integration functionality | Secondary | Primary | As Needed
| Unit Test | 27 | Design/Execute unit tests on developed code | Secondary | Primary | As Needed
| Functional Test | 28 | Design/Execute functional tests on deployed environments | Primary | Secondary | As Needed
| Integration Test | 29 | Design/Execute integration tests on integrated environments with converted data | Secondary | Primary | As Needed
| UAT / E2E Test | 30 | Design/Execute end-to-end tests with converted data | Primary | Secondary | As Needed
| Regression Test | 31 | Build, maintain, and execute the regression test suite | Primary | Secondary | As Needed
| Data Conversion | 32 | Build and maintain data conversion routines to migrate data from the legacy environment to new system(s) | Secondary | Primary | Secondary
| Organizational Change Management | 33 | Identify transformation required to business/operational roles and responsibilities - define the organizational and R&R changes and the transition approach | Primary | As Needed | As Needed
| Training |  | Develop and deliver training as needed to support the OCM transition and rollout of new systems/features | Primary | As Needed | As Needed
| Implementation/cutover | 34 | Execute one-time implementation activities required to go-live and transition ownership of the system to the operational team for each phase | Secondary | Primary | Secondary
Infrastructure | Hardware | 35 | Maintain project-required servers and devices | Primary | Secondary | As Needed
| Tools | 36 | Maintain, configure project tools | Primary | Secondary | As Needed
| Environments | 37 | Create and maintain development, test, and other project environments | Primary | Secondary | As Needed
| Code Management |  | Design and deliver strategy to manage multiple codebases | Primary | Secondary | Secondary
| Deployment | 38 | Automate or manually deploy developed code to project environments | Secondary | Primary | As Needed
| Support | 39 | Troubleshoot technical issues related to servers, performance, downtime, etc. | Secondary | Primary | As Needed
| Security / data protection | 40 | Manage access to confidential/PII/HIPAA/etc. data | Secondary | Primary | Secondary
| Business Continuity / Disaster Recovery | 41 | Define and maintain disaster recovery procedures to ensure disruption events have a minimal impact on project/production execution | Secondary | Primary | Secondary
| Network Services | 42 | Design, build, and maintain the network supporting project/production environments | Primary | As Needed | As Needed