Iowa Communications Network

OSP Log # 97220101, Link 1201(36f), 1204(24f), 1201A(12f), 1202(8f), 1201D(4f)

Woodbury Co., Hwy 20 Fiber Relocate

Overview of the Project:

ICN will need to relocate approximately 1.7 miles of fiber along Hwy 20 in Woodbury Co., due to a DOT paving project. Said project is from the Hwy 20 – Hwy 75 interchange East to Carroll Ave., with an additional 890’ along Buchanan Ave. All work to be completed per the attached STANDARD INSTALLATION REQUIREMENTS and TYPICALS except where noted within this STATEMENT OF WORK (SOW).  Upon notification of completion, the ICN will perform a review using the attached PUNCHLIST.  Any corrections will need to be made prior to ICN issuing payment for work completed.

SPLICING EXCLUDED FROM THIS CONSTRUCTION BID

SPLICING SHALL BE COORDINATED WITH NOC OSP

Preparatory Tasks & Responsibilities:

- Secure all necessary locates from “Iowa One Call.”

- Construction signing shall comply with the Manual on Uniform Traffic Control Devices.

Duct Installation

- Provide one 1 1/4 inch diameter HDPE, SDR 13.5 duct as noted on plans (approximately 9470’)

- Provide one 2 inch diameter HDPE, SDR 13.5 duct as noted on plans (approximately 890’)

- It shall be the sole responsibility of the contractor to ensure that the fiber installation is in the public Right-of-Way. See engineering plans for locations and distances off existing public ROW when provided.

- Bore at depths called out on the plans for clearance under waterways, paved roads, future grading, and future culverts.

- The contractor shall use a clamp-on, crimp-on, or compression type duct coupler for all duct splices. The coupler will be of a type specifically designed for telecommunications duct. The contractor will be required to provide ICN a 24 hr notice for splice inspection and recording the GPS location prior to backfill (unless other arrangements have been made).

- Ensure that a pull rope (Mule Tape) is left in all duct.

Handholes:

- Install twelve ICN provided 24”x36”x 36”  hand holes at the locations shown on the plans and relocate one handhole  per ICN standards  (Sta. 553+32) . Install ROW markers at HH’s where no locate ped will be placed.

Fiber Exposure:

- Expose 50’ of existing fiber at West end of project and 100’ at the South end of Buchanan Ave. Assist splicer on cut over night with pull back of existing fiber per plans.

- Coordinate the exposure of the existing fiber and trench excavation with ICN. This work to occur the afternoon prior to cut over with backfill the following day. Place orange construction safety fence with steel posts around open excavations.

Fiber Installation

- Install a  12,610 foot ICN provided, armored 48-strand single mode fiber between the proposed hand holes.  Place100’ slack coils in all hand holes.

Locate Facilities:

- Install an ICN supplied Tri-View locate ped, ground rod, ground clamp with ground wire at Buchanan Ave. and                Carroll Ave. as shown on the plans.

ICN Provided Materials per attached table: Contractor shall pick up ICN-provided materials at the ICN warehouse in Des Moines.  Contact the ICN warehouse 48 hours in advance to pick up materials; contact Paul Damge (515-725-4749) to ensure

availability.

Contractor shall supply all other materials required for proper installation, including but not limited to: HDPE, Grounding and Tracer Wires, Rock, Wire Mesh, mule tape, etc.

ICN Responsibilities:

- Project Management

- ICN provided materials; see plans and/or materials list.

- DOT permit

ICN Points of Contact for this Project:

Engineering/Design:

Chris Harris

515-725-8925 office

515-380-3689 cell

Materials:

Paul Damge

515-725-4749 office

515-491-1429 cell

Splice Coordination: (typically a minimum of 2 weeks notification is required)

ICN Network Operations Center (NOC)

515-725-4400

800-572-3940

Other Points of Contacts:

- N/A

Bid/Job Showing: N/A

Work Start Date: Work may begin upon award of the bid and completion of the contract. Only written modifications to this Scope of Work are binding - Verbal changes to this scope of work by any person or persons are not binding, unless confirmed in writing.

Completion Date: Not later than April 28th, 2023 (extension may be negotiated based upon weather and/or unforeseen construction problems in the ROW)

Quotes Due Date:

Quotes must be received by Sheri Stephens, ICN Contracting, NLT 2PM on March 30th, 2023

Quotes:

Contractors must submit a quote for Construction Bid as outlined in the SOW and per the Engineering drawings.  ICN requires a breakdown of lump sum bids into labor and materials. Quotes must be received by Sheri Stephens, ICN Contracting, on or before the due date shown with the bid announcement (“Invitation to Bid”).  .

Completion of Work:

- Upon notification of construction completion, ICN will have 2 weeks to complete the Punch List.

- Upon initial completion of Punch List, the Contractor will have 2 weeks to correct any issues identified on the Punch List.

- Upon notification of corrections, the ICN will have 1 week to verify corrections were completed to the ICN’s satisfaction.

- No payment will be made until all work is completed per the contract unless agreed upon by both parties.

Attachments:

97220101 - DOT documents

97220101 – Engineering plans

97220101 – Punch list

97220101 – Typicals

97220101 – SOW scope work (this document)