## Task List
Identifying the Requirement |  | Responsible Party | Due Date | Date Completed
| Identify Requirement | Agency | 2017-10-02 | 2017-12-20
| Create list of specificiations | Agency | 2017-10-02 | 2017-12-20
| Meet with Purchasing | Agency
| Evaluation committee agreements completed | Agency
Forming The RFP
| Purchasing agent drafts RFP | DAS Procurement | 2018-01-12 | 2018-01-25
| Rough draft of RFP sent to Department | DAS Procurement | 2018-01-12 | 2018-01-25
Finalizing the RFP
| Review rough draft of RFP | Agency |  | 2018-03-02
| Submit changes to Purchasing | Agency |  | 2018-03-05
| Purchasing Agent creates RFP final draft | DAS Procurement | 2018-03-08 | 2018-03-29
Solicitation of Proposals
| Post to TSB site | DAS Procurement | 2018-03-29 | 2018-03-29
| Vendors added to bidders list | DAS Procurement | 2018-03-31 | 2018-03-29
| RFP posted and sent. | DAS Procurement | 2018-03-31 | 2018-03-31
| Questions received from vendors | DAS Procurement | 2018-04-13 | 2018-04-13
| Responses to questions writen | Agency/DAS Procurement | 2018-04-15 | 2018-04-15
| Points determined for scoring criteria | Agency/DAS Procurement | 2018-04-23 | 2018-04-23
| Addendums posted | DAS Procurement | 2018-04-16 | 2018-04-25
| Proposals received | DAS Procurement | 2018-04-27 | 2018-04-27
Evaluation of Proposals
| Send COI and NDA to eval committee | DAS Procurement | 2018-04-27 | 2018-05-02
| Proposals given to requester for evaluation | DAS Procurement | 2018-04-30 | 05/04/208
| Proposals evaluated | Agency/DAS Procurement | 2018-05-18 | 2018-05-04
| Presentations scheduled | DAS Procurement | N/A | N/A
| Presentation 1 | Agency/DAS Procurement | N/A | N/A
| Presentation 2 | Agency/DAS Procurement | N/A | N/A
| Presentation 2 | Agency/DAS Procurement | N/A | N/A
| Final evaluation | Agency/DAS Procurement | 2018-05-25 | 2015-05-24
| Winning proposal determined | Agency/DAS Procurement | 2018-05-26 | 2015-05-24
Forming an Agreement
| Final agreement negotiated by Purchasing | DAS Procurement | 2018-06-01
| Final agreement written by Purchasing | DAS Procurement | 2018-06-01
| Agreement signed by company | DAS Procurement | 2018-06-01
| Agreement signed by Department | Agency | 2018-06-01

## Checklist
Abstract of Technical Proposals |  |  |  |  | ü
| Carestream Health | Advanced Detection Solutions | Lodox NA LLC | GE Healthcare
Proposal Contact: | Sara Pyatt | Christian Chahine | Adam Harris | Jason Blythe
Ph: | 651-338-6263 | 949-500-6298 | 440-210-3030 | 309-230-1323
Email: | sara.pyatt@carestream.com | Christian@detection-soultions.com | Adam.Harris@Lodox.com | Jason.Blythe@ge.com
Original and (2) copies | ü | ü | ü | ü
Copy on CD (Drive | ü | ü | ü | ü
Separately Sealed Cost Proposal | ü | ü | ü | ü
(3) References | ü | ü | ü | ü
Subcontractors | ü | ü | ü | ü
Positive statement to T&Cs | ü | ü | ü | ü
Certification Letter | ü | ü | ü | ü
Release Authorization | ü | ü | ü | ü
Pt by Pt Response to Section 4 | ü | ü | ü | ü
Form 22 Signed | ü | ü | ü | ü
sam.gov | ü | ü | ü | ü
SOS.iowa.gov | ü | ü | ü | ü
ACCEPT / REJECT: | ACCEPT | ACCEPT | ACCEPT | ACCEPT

## Scoresheet
RFP0318588020 - Score Sheet |  |  | Carestream Health |  | Advanced Detection Solutions |  | Lodox NA LLC |  | GE Healthcare
Mandatory requirements |  |  | Pass/Fail |  | Pass/Fail |  | Pass/Fail |  | Pass/Fail
|  |  | Quote - 346743 | [5 empty] | XR650 ONLY
Equipment Capability Specifications
4.1.1.1 Equipment shall be able to produce a single full body scout image or have the ability to stitch multiple images together either lengthwise (head to foot) or laterally (side to side) to create a full body image. |  |  | pass |  | pass |  | pass |  | pass
4.1.1.2 Equipment shall be able to adjust the table or shall have a tabletop that is able to float. |  |  | pass |  | pass |  | pass |  | pass
4.1.1.3 Equipment shall have a minimum bariatric weight capacity above five hundred pounds. |  |  | pass |  | pass |  | pass |  | pass
4.1.1.4 Equipment shall be able to interface with other programs and databases including Health Level-7 (HL7) and Digital Imaging and Communications in Medicine (DICOM). |  |  | pass |  | pass |  | pass |  | pass
4.1.1.5 Equipment shall offer DICOM capable image archiving options. |  |  | pass |  | pass |  | pass |  | pass
4.1.1.6 Respondent shall provide background checks required for anyone working on the resulting Master Agreement, implementation and maintenance. Background check requirements apply to any Respondent employee who will be onsite working on the installation, maintenance, and implementation, training and any employee one that would be remoting into the machine for future repair and maintenance. |  |  | pass |  | pass |  | pass |  | pass
Criterion | Using Response(s) to RFP Section(s) among others: | Possible Points (weight) | Score on scale of 1 - 10 | Actual Points Scored | Score on scale of 1 - 10 | Actual Points Scored | Score on scale of 1 - 10 | Actual Points Scored | Score on scale of 1 - 10 | Actual Points Scored
Executive Summary and Vendor Background | 3.2.2 & 3.2.4 | 130 | 9 | 117 | 5 | 58.5 | 9 | 117 | 2 | 26
Experience and References | 3.2.5 & 4.4 | 130 | 7 | 91 | 3 | 27.3 | 8 | 104 | 3 | 39
Equipment Specifications | 4.2.1 | 150 | 8 | 120 | 3 | 36 | 7 | 105 | 5 | 75
Image Processing | 4.2.2 | 140 | 8 | 112 | 1 | 11.2 | 7 | 98 | 5 | 70
Support | 4.2.3 | 130 | 9 | 117 | 2 | 23.4 | 8 | 104 | 6 | 78
Optional Specifications | 4.3 | 20 | 8 | 16 | 3 | 4.8 | 5 | 10 | 5 | 10
| minimum score of 420 | 700 | SUBTOTAL | 573 | SUBTOTAL | 161.2 | SUBTOTAL | 538 | SUBTOTAL | 298
Cost Points Available |  |  | Tech pts/Tech pts available | Maximum Cost Points | Tech pts/Tech pts available | Maximum Cost Points | Tech pts/Tech pts available | Maximum Cost Points | Tech pts/Tech pts available | Maximum Cost Points
300
Cost Points Total |  | Lowest Price |  | Respondent Cost |  | Respondent Cost |  | Respondent Cost |  | Respondent Cost
|  | 219348.6 |  | 219348.6 |  |  |  | 537500
|  |  | SUBTOTAL | 300 | SUBTOTAL | 0 | SUBTOTAL | 122.4271 | SUBTOTAL | 0
Total
|  |  | TOTAL SCORE: | 873 | TOTAL SCORE: |  | TOTAL SCORE: | 660.4271 | TOTAL SCORE:

## Cost Analysis
| Carestream Quote | Lodox
Equipment | 134498.52 | 445000
Imaging Processing |  | Included
Equipment Support | 11550 | Included
Annual Maintenance
Year 1 | 5000 | 18500
Year 2 | 17075.02 | 18500
Year 3 | 17075.02 | 18500
Year 4 | 17075.02 | 18500
Year 5 | 17075.02 | 18500
| 219348.6 | 537500
| 219348.6 | 537500

## Bid Comparison
RFP Evaluation Score Sheet
| Carestream Health | Advanced Detection Solutions | Lodox NA LLC | GE Healthcare
Proposal Scoring
Tech Proposal | 573 | 161 | 538 | 298
Cost Proposal | 300 | N/A | 122 | N/A
Total Points | 873 | 0 | 660 | 0